## CLSU SP
CLSU 2015 OPERATIONAL PLAN
GOALS/THRUSTS/STRATEGIES |  | PROGRAMS and PROJECTS |  | TARGETS and MILESTONES | QUARTERLY TARGET IMPLEMENTATION |  |  |  | LEAD PROGRAM | ACTUAL ACCOMPLISHMENTS AS OF 31 DEC 2015 | PERCENTAGE (%) | OTHER ACCOMPLISHMENTS
[5 empty] | Q1 | Q2 | Q3 | Q4
Objective A: IMPROVE EFFICIENCY
1.0 RATIONALIZING INSTITUTIONAL GOVERNANCE
1.1 | Mapping of Programs | a. | Identify areas of program duplication and those which are over served/underserved | Areas with program duplication identified | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Underserved and over served programs monitored and regulated | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Identify areas not adequately covered by the private and existing HEIs within CLSU's service area (Region III) | Number of programs not covered by private/existing HEIs w/in Region III identified | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
1.2 | Re-engineering of Programs | a. | Strengthen students capability to start entrepreneurial projects in selected courses and skills training for students | Sentro ng Wika at Kultural approved and operationalized | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Mathematics Center approved and operationalized | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Laboratory of Environmental and Analytical Chemistry approved and operationalized | x | x | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | i-care operationalized (Innovation Center for Agriculture and Related Enterprises) | x |  |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Private-Publice Partnership in Entrepreneurship Established | x |  |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Cag One-Stop Entrep Shop established and operationalized |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  | b. | Enhance diploma courses/ special courses (specialized skills) | NC II & III Assessment Center established |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Diploma in Dairy Science and Entrep approved and implemented |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Other certificate examination like NC IV - Programming passed by BSIT students |  | x |  | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Offering of the BSIT in ladderized format; granting of Associate in Computing Technology after two years |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  | c. | Expand non-formal education programs for capability building and empowerment | Toddler Center established |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Agrikulturang Pinoy Rice Laboratory Established & Operationalized |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | OBE compliant instructional materials developed and reproduced | x |  |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Proficiency Program in Mathematics, English and Filipino established |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
1.3 | Piloting of Governance and Restructuring Models | a. | Develop the CLSU Master Plan | CLSU Master plan approved |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Participate in the amalgamation efforts of CHED | Required reports and documents provided | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | c. | Restructure CLSU's OMS | OSA OMS restructured | x |  |  |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Center for International Affairs established |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Center for Socio-Cultural Affairs established |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Rationalization study/plan for the College of Arts and Sciences, College of Engineering, ISPEAR, CERDS, and academic IGPs conducted |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Manual of Operations and process flow for GASS offices updated |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
|  |  |  | Center for Management Information System established |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Quality Assurance Office established | x |  |  |  | GENERAL ADMINISTRATION PROGRAM
|  |  |  | CAG OMS restructured to suit current trends and demands |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
2.0 RATIONALIZING PROGRAM OFFERINGS
2.1 | Typology | a. | Re-engineer CLSU towards becoming a Research University | All criteria for research university-hood provided in CMO 46, s. 2012 satisfied | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Cutting-Edge Research embedded in all agri Programs |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  | b. | Streamline academic program verticalized operations | University and College Graduate Education Coordinating Offices established |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  | c. | Re-engineer the non-degree specialized courses, undergraduate and graduate education program to international standards | Curriculum mapping of the different degree programs completed upon released of CHED CMOs | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | OBE curricula in all courses harmonized and implemented in conformity with international standards | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | International graduate programs (research based curricula) offered |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  | d. | Implement equivalency program (trainings and experiences for MS degree equivalency) under ETEAAP | Degree offerings under ETEAAP expanded |  |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  | e. | Review typologies of present curricular programs to find out the market appeal to prospective students | OBE standards adopted to enrich curricular programs |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  | f. | Offer "palatable" courses such as BS in Biotechnology under the Department of Biology or Life Sciences | Presentation, approval and implementation of new degree programs | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
2.2 | CLSU Leveling | a. | Review performance covering areas relative to programs, functions and operations focusing on the quality and relevance of instruction, research capability and outputs, relationship with and services to the community, and management of resources | Matching review of leveling criteria in all colleges completed |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  | b. | Review/phase-out/closure of inefficient/duplicative programs | Inefficient/duplicative programs reviewed, closed or phased out | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
2.3 | Development of Priority Programs | a. | Implement special programs on the MDGs, environmental awareness, disaster, risk reduction and management, natural resource management and gender and development | Disaster Preparedness Program implemented | x | x | x | x | RET PROGRAM
|  |  |  | Household Socio-Economic Development: 4Ps Program implemented |  | x | x |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Gender and Development Program implemented | x | x | x | x | RET PROGRAM
|  |  |  | Special Program for Persons with Disabilities, Solo Parenting and Students with Special Needs implemented | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Implementation of the National Greening Program | x | x | x | x | RET PROGRAM
|  | b. | Formal approval with MOA/MOU of all outreach, training and extension programs by the administration or ADCO | Academic exchanges, outreach, training and extension programs have approved MOA/MOU |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
3.0 RATIONALIZING RESOURCE UTILIZATION AND MAXIMIZING RESOURCE UTILIZATION
3.1 | Normative Financing | a. | Expand implementation of the NFF to program level to minimize impact of cross-subsidy | NFF implemented to all programs |  | x |  | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Rationalize resource distribution | Policies and guidelines established |  | x |  |  | GENERAL ADMINISTRATION PROGRAM
3.2 | Assets Inventory and Management of Resource Generation | a. | Expand the income generating capability of existing projects | Incentives to project managers, laborers and management staff provided |  |  | x |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Two UBAP personnel have undergone training and immersion per year |  | x |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | One investment forum conducted per year |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  | b. | Study the feasibility of highly profitable business projects through partnership with the private sector | Organic and aromatic varieties of brown rice produced |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | One flatbed dryer purchased |  | x |  |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Rice Modernization Project |  | x |  |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | New feed milling machine purchased, installed and tested |  | x | x | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | NPO storage house rehabilitated | x |  |  |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Feed and Grains Processing Center (FGPC) roofing repaired |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | Concreting of 1,000 sq.m. solar dryer completed |  | x |  |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Construction of one additional tunnel ventilated broiler house with 24,000 bird capacity completed |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | Uniform project implemented |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | Construction of showroom for AFTBI products completed |  | x |  |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Processed products for chevon, tilapia and bottled juice commercialized | x | x | x | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | In wall incubatees recruited | x |  | x |  | BUSINESS AFFAIRS PROGRAM
|  | c. | Review and rationalize physical resource utilization | Hybrid rice produced in partnership with SL Agritech | x | x | x | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | Swine Project transferred to area near BFAR |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | Partnership with Good Samaritan Hospital established |  |  | x |  | BUSINESS AFFAIRS PROGRAM
|  |  |  | Joint venture with CLSU Alumni established |  |  |  | x | BUSINESS AFFAIRS PROGRAM
|  |  |  | Agricultural Machinery Manufacturing project established (lease or joint venture) |  |  |  | x | BUSINESS AFFAIRS PROGRAM
Objective B: UPGRADE QUALITY
4.0 STRENGTHENING QUALITY ASSURANCE
4.1 | Accreditation | a. | Work for QS World University Ranking | Committee formed to study World Ranking | x |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  | b. | Accreditation of programs by international and national accrediting associations or agencies | AB Social Science, BS Statistics, BS Food Technology, BS Textile and Garment Technology accredited Level III |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | AB Dev't Comm., BSIT, MS Biology, Master in Biology, Master in Chemistry accredited Level II |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Graduate programs in Agriculture accredited Level IV Phase I |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | BSF Level IV Phase II accredited, and MS and PhD Aquaculture Level IV Phase I accredited |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | BSA and BSAb accredited Level IV Phase II | x |  |  |  | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Level I accreditation of the ABLL program | x |  |  |  | ACADEMIC AFFAIRS PROGRAM
|  | c. | Degree program review and revision vis-à-vis outcome-based education (OBE), typology and quality assurance | All degree programs reviewed and revised |  | x |  | x | ACADEMIC AFFAIRS PROGRAM
|  | d. | International benchmarking of various curricular programs | International benchmarking activities undertaken |  | x |  | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | BSA program offerings matched with ASEAN AIMS universities and UMHP | x | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  | e. | Twinning program with reputable international institutions | Twinning program with reputable international institutions established |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  | f. | ISA/ISO accreditation for standardization | ISA/ISO Manual developed |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | 5S implemented |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
4.2 | Monitoring and Evaluation for Quality Assurance | a. | Develop Quality Management System (QMS) | QMS Manual developed, reviewed and implemented |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Implement Strategic Performance Management System (SPMS) | SPMS implemented | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | c. | Improve the percentage passing of graduates in licensure examinations through the LEAP and conduct mentoring classes | Continuing implementation of LEAP and conduct of mentoring classes | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | d. | Assess examinees/graduates to identify problem areas | Continuing assessment of examinees/ graduates |  | x |  | x | ACADEMIC AFFAIRS PROGRAM
5.0 UPGRADING QUALIFICATIONS OF FACULTY
5.1 | Reinvigorate Scholarship Program | a. | Update Faculty and Staff Development Program | Faculty and Staff Development Program updated |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
5.2 | Continuing Professional Education Program | a. | Increase funding for faculty and staff development and expand benefits | Continuing efforts to increase funding for faculty and staff development and expansion of benefits | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Research grants for full professors | Continuing support for research grants for full professors | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | c. | Membership to professional organizations | Continuing funding support to encourage membership to professional organizations | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | FAC as member of the American Tilapia Association |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Membership of 6 faculty and staff to professional organizations |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  | d. | Engagement in consultancy services | Five faculty and staff tapped for consultancy services per year |  | x |  | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Participation of 2 researchers in public-private partnership |  | x |  | x | RET PROGRAM
|  | e. | Increase faculty involvement to research and publication of outputs in refereed journals | 3% yearly increase in the number of faculty with research outputs and publication in referred journals ensured |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  | f. | Benchmarking to other universities abroad and other R&D Centers | Continuing benchmarking to other universities and R&D centers at 4 visits per year |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
5.3 | Merit Selection and Promotion | a. | Filling-up of faculty vacant positions with highly qualified recruits | Continuing efforts to attract highly qualified recruits to fill-up vacant faculty positions | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  |  |  | Priority hiring of graduates with academic honors or hire faculty with MS degree | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Policy to hasten promotion for faculty who have achieved the professorial level | Policy on promotion of faculty who achieved professorial level approved and implemented | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | c. | Implement NBC 461 evaluation results | Continuing implementation of NBC 461 evaluation results | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
6.0 UPGRADING CLSU TO INTERNATIONAL STANDARDS
6.1 | Upgrading and Modernization of Infrastructure Facilities and Equipment | a. | Establish state-of-the-art research, training and extension facilities for international participants, top-level and middle executive development trainings | Laboratories constructed: Plant Pest Diagnostic Laboratory; Post-Harvest, Food Processing and Seed Technology Laboratory; Soil and Water Laboratory; Analytical Service and Instrumentation Laboratory | x | x | x |  | RET PROGRAM
|  |  |  | Laboratories constructed: Mushroom Gene bank; Laboratory for Environmental Analytical Chemistry (LEACH); Laboratory of Environmental Nanotechnology and Sensors (LENS) | x | x |  |  | RET PROGRAM
|  |  |  | Laboratories constructed: Engineering Laboratory Building; Land and Water Field Laboratory | x | x |  |  | RET PROGRAM
|  |  |  | Entrep Laboratory and Showroom constructed | x |  |  |  | RET PROGRAM
|  |  |  | Continuing rehabilitation and improvement of training and extension facilities (Training Dorm, WRMC Hall, PCC Training quarters) | x | x | x |  | RET PROGRAM
|  |  |  | Upgrade and rehabilitation of RM-CARES (fencing, net houses, water tank and irrigation system, bio-pesticides lab, storage) | x |  |  |  | RET PROGRAM
|  |  |  | PCC at CLSU Semen Processing Laboratory, Nutrition Laboratory and other facilities, deep well at the National Bull Farm rehabilitated | x |  |  |  | RET PROGRAM
|  |  |  | Israeli greenhouses, shade houses, pond system/production ponds repaired | x | x |  |  | RET PROGRAM
|  |  |  | Forage Seed Processing Laboratory established | x |  |  |  | RET PROGRAM
|  |  |  | WRMC GIS Center, Water Quality Laboratory and Soil Laboratory established | x | x |  |  | RET PROGRAM
|  | b. | On-line promotion of academic, research, extension and training programs | On-line promotion of academic, research, extension and training programs thru creation of center website | x | x | x | x | RET PROGRAM
|  |  |  | Developed electronic copies of IEC materials for dissemination | x | x | x | x | RET PROGRAM
|  | c. | Purchase of vehicles for academic, research, extension and training purposes | Two school bus purchased; two coasters purchased |  |  |  | x | RET PROGRAM
|  | d. | Provision of generators | Two generator sets purchased per year |  |  |  | x | RET PROGRAM
6.2 | COE and COD Programs | a. | Implement programs as COE/COD and NUCAF | COE/COD programs maintained | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Increase the number of COE/COD programs | Programs applied as COE/COD | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
6.3 | Internationalization | a. | Participation in the ASEAN International Mobility for Students (AIMS) | Partnership with one international university established per year |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Twinning and benchmarking with reputable international universities | Twinning program with reputable international institutions established |  |  |  | x | ACADEMIC AFFAIRS PROGRAM
6.4 | Establish Specialized Centers and Platforms for R& D Implementation | a. | Implement cutting-edge research at the college level | Upgrading and Strengthening the University's Research Capabilities in the Breeder Sciences (UPSURGE Project) | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Enhancement of Engineering Laboratories in Preparation for the Implementation of the Outcome-Based Education (OBE) System (Engineering OBE Project) | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Veterinary Learning Center for Epidemiology and Animal Diseases Diagnostics (VET-LEAD Project) | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  |  |  | Agricultural Education Enhancement Through Science and Technology for Readiness to Global Economic Integration (AGRI-EDU S & T Project) | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Develop new and improved processes, systems, products and technologies | One approved IPR per year |  |  |  | x | RET PROGRAM
|  |  |  | Improved/reformulated organic inputs which are PNS compliant | x |  | x |  | RET PROGRAM
|  |  |  | Improved production and post harvest technologies for selected crops | x |  | x |  | RET PROGRAM
|  |  |  | Developed locally fabricated field test kit for the detection of mastitis in goats |  |  |  | x | RET PROGRAM
|  |  |  | Developed a locally fabricated irrigation controller |  |  |  | x | RET PROGRAM
|  |  |  | Research for Development approach: comparison of previous and current generation of FaST for continuous improvement |  |  |  | x | RET PROGRAM
6.5 | Upgrading of R&D programs | a. | Intensity dissemination and utilization of R&D outputs | 1% increase on the number of R&D outputs utilized and commercialized |  |  |  | x | RET PROGRAM
|  |  |  | Developed modules, sourcebook, audio-visual and print materials | x | x | x | x | RET PROGRAM
|  |  |  | Packaged, produced and promoted new/improved technologies |  | x |  | x | RET PROGRAM
|  |  |  | Techno demo and piloting of organic rice, vegetable production, organic onion and mango production to 4 pilot barangays per year | x |  |  |  | RET PROGRAM
|  |  |  | Techno demo and piloting of forage production modules/goat production to 2 pilot barangays per year | x |  |  |  | RET PROGRAM
|  | b. | Continue capability building and empowerment | BIDANI implemented in 3 barangays per year in partnership with the Science City of Munoz |  | x |  |  | RET PROGRAM
|  |  |  | Conduct 35 trainings per year for farmers, teachers, extension workers and other organic practitioners | x | x | x | x | RET PROGRAM
|  | c. | Implement special programs and projects | Carabao Development Program for agriculture support services | x | x | x | x | RET PROGRAM
|  | d. | State-of-the-art R&D equipment | Continuing purchase of state-of-the-art R&D equipment |  | x |  | x | RET PROGRAM
|  | e. | Increase research partnerships with private corporations | Two partnership with private corporation established per year |  |  |  | x | RET PROGRAM
|  | f. | Maximize utilization of the advances in information technology | CLSU website enhanced/upgraded |  |  | x |  | RET PROGRAM
|  | g. | Promote S&T based or technology-based enterprises | Five new S&T farms identified per year |  | x |  | x | RET PROGRAM
Objective C: ENHANCE ACCESS TO QUALITY EDUCATION
7.0 MODERNIZING FACILITIES
7.1 | Infrastructure Development and Facilities Upgrading | a. | Improve domiciliary facilities, road system, power and water supply system, ICT system | Facilities improved | Details contained in the 2014-2018 Facilities Development Plan |  |  |  | GENERAL ADMINISTRATION PROGRAM
7.2 | ICT Infrastructure Development | a. | Implementation of the Comprehensive CLSU IT Plan | Comprehensive CLSU IT Plan finalized, approved and implemented | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Implementation of collection and enrolment system via PhPay | Collection and enrolment system via phPay (thru Landbank) |  | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | c. | Fiber optic cabling interconnection of Academic Affairs Building, Administration Building and Colleges | Fiber optic cabling interconnection established |  | x | x | x | ACADEMIC AFFAIRS PROGRAM
7.3 | Digitization and Automation of Operation in Line with GIFMIS | a. | Digitization of student, personnel and property records | Student, personnel and property records digitized |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Adopt e-bidding | e-bidding adopted |  |  | x |  | GENERAL ADMINISTRATION PROGRAM
|  | c. | Implement APCPI results | APCPI results implemented | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
8.0 STRENGTHENING STUDENT FINANCIAL ASSISTANCE PROGRAM
8.1 | Strengthen and Expand Student Assistance Programs | a. | Liberalize admission requirements for incoming students and mobile recruitment in high schools | Admission requirement liberalized for incoming students |  | x |  | x | ACADEMIC AFFAIRS PROGRAM
|  | b. | Expand fund-sourcing for scholarship program for the poor and deserving students | Continuing fund-sourcing for scholarship programs | x |  | x |  | ACADEMIC AFFAIRS PROGRAM
|  | c. | Expand student assistantship, offer opportunities for students to earn while studying or learning | Student part-time employment program approved and implemented | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
8.2 | Improving Student Services | a. | Establish system for supporting, monitoring, and evaluating services to enable students to graduate on time | System established and implemented |  | x |  |  | ACADEMIC AFFAIRS PROGRAM
|  | b. | Enhance leadership capabilities of students through leadership trainings, conferences, and student-initiated projects | Continuing leadership training for students and conduct of student activities/projects | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | c. | Strengthen Guidance and Counseling Program for students with special needs, PWDs and other special groups | Conduct of survey and profiling of students with special needs, PWDs, and other special groups | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
|  | d. | Enhance special skills/talents of student in sports and performing arts through sports development program, cultural trainings and performances. | Improved performance in sports and cultural competitions | x | x | x | x | ACADEMIC AFFAIRS PROGRAM
9.0 STRENGTHENING INSTITUTIONAL MANAGEMENT CAPABILITY
9.1 | Shared Management | a. | Sharing and distribution of management responsibility and accountability | Faculty and staff involved in management through committee assignments | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Council of Deans and Directors | Optimum participation of stakeholders in the management of the four programs through regular monthly meetings | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
9.2 | Values Orientation | a. | Develop desirable work ethics and values | Orientation on RA 6713, Values and ISO 9001:2008 | x | x | x |  | GENERAL ADMINISTRATION PROGRAM
9.3 | Creating an Optimal Workplace | a. | Program on Rewards and Incentives for Service Excellence (PRAISE) | PRAISE implemented | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Employee benefit/provident fund program | Employee benefit/provident fund developed and implemented |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
|  | c. | Social, Cultural and Sports Program | Team building, social, cultural and sports activities conducted | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  | d. | Conflict Management and Mediation Program | Conflict Management and Mediation Program implemented |  |  |  | x | GENERAL ADMINISTRATION PROGRAM
9.4 | Capacity Enhancement Programs | a. | Employee Development Program | Seminar-Workshop on Outcome-Based Education | x | x | x | x | GENERAL ADMINISTRATION PROGRAM
|  |  |  | Seminar-Workshop on Excel Application (Level 2) | x |  | x |  | GENERAL ADMINISTRATION PROGRAM
|  |  |  | Seminar on Frontline Service and Enhancing Customer Satisfaction |  | x |  | x | GENERAL ADMINISTRATION PROGRAM
|  | b. | Accreditation as Training Provider | Renewed accreditation as Training Provider by DILG (LoGoTri) and CDA |  |  | x |  | RET PROGRAM
|  |  |  | Renewed certification by the Organic Certification Center of the Philippines (OCCP) |  |  | x |  | RET PROGRAM
|  | c. | Enhancing FITS and Environment Implementers | FITS implementers trained | x |  | x |  | RET PROGRAM
TOTAL